## FY21 Proposed BudgetCD_JB_JR_CC
Capital and Grants: 1 Year Delay Project List by COB Monday, June 1, 2020 Instructions: In column H, please select "Likely" or "Unlikely", depending on whether you believe the project will be delayed for 1 year (regardless of reason). The District is considering delaying Capital Projects for 1 year to improve our financial position by reducing the capital budget contribution amount. If a project is selected as "Likely", "FY21 Savings $" amounts in Column I and "FY21 Grant $ Impacted" amounts in column J will populate automatically.
Division | Project ID | Project Description | FY21 Budget Book Status | Total Project Budget (For FY21 Program) | FY21 Budget | Suggested Responsible* | Select Likely/Unlikely | FY21 Savings $ | FY21 Grant $ Impacted | FY21CYDistrict | FY21CYFederal | FY21CYState | FY21CYOther | FY21CYGrants | FY21CYTotal | District Contribution to Project | Explanatory Notes
BRIDGE | 2129 | Capital Equipment (FY21) | Capital Equipment | 1742000 | 1742000 | Jennifer/Chi | Unlikely | 0 | 0 | 1742000 | 0 | 0 | 0 | 0 | 1742000 | 100%
BRIDGE | 1921 | Stores Bldg Office Space HVAC Replacement | FY21 - Continuing Projects | 35000 | 20000 | Jennifer/Chi | Unlikely | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 100% | Replacement is needed
BRIDGE | 2020 | Bridge Admin Office Improvements | FY21 - Continuing Projects | 122000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
BRIDGE | 1920 | Alexander Avenue Slope Strengthening Des/Env | FY21 - Continuing Projects | 500000 | 50000 | Jennifer/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
BRIDGE | 1422 | FASTRAK Equipment Upgrade | FY21 - Continuing Projects | 1000000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
BRIDGE | 1821 | IS Data Center Seismic Retrofit | FY21 - Continuing Projects | 1500000 | 50000 | Jennifer/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Mitigate risk by moving occupants or not replaceable equipment outside of building.
BRIDGE | 1722 | Toll Plaza Pavement Overlay | FY21 - Continuing Projects | 3500000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
BRIDGE | 1118 | Suicide Deterrent - Design | FY21 - Continuing Projects | 5543101 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Are there fabrication and material testing delays from COVID-19?
BRIDGE | 1525 | Toll System Upgrade | FY21 - Continuing Projects | 8480848 | 500000 | Jennifer/Chi | Unlikely | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 100%
BRIDGE | 1820 | Toll Plaza Gantry - Des/Con | FY21 - Continuing Projects | 7264000 | 500000 | Jennifer/Chi | Unlikely | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 100%
BRIDGE | 9826 | Main Cable Access | FY21 - Continuing Projects | 13180000 | 100000 | Jennifer/Chi | Likely | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 100000 | 100% | The main cable access may be essential project to maintain the bridge.
BRIDGE | 1526 | Suicide Deterrent - Construction | FY21 - Continuing Projects | 192779868 | 30000000 | Jennifer/Chi | Unlikely | 0 | 0 | 9369973.2692 | 19474025.1612 | 1089325.3646 | 66676.205 | 20630026.7308 | 30000000 | 31.23% | Are there fabrication and material testing delays from COVID-19?
BRIDGE | 2120 | Trailer F Replacement | FY21 - New Projects | 145000 | 27000 | Jennifer/Chi | Likely | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 27000 | 100%
BRIDGE | 2121 | Toll Plaza Admin Bldg Elevator Replacement | FY21 - New Projects | 590000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
BUS | 2139 | Capital Equipment (FY21) | Capital Equipment | 338000 | 338000 | Jacob/Chi | Unlikely | 0 | 0 | 338000 | 0 | 0 | 0 | 0 | 338000 | 100% | Many capital equipment purchases are critical to operations and will likely need to happen; though we could ask Divisions to limit purchases to essential items
BUS | 1932 | Zero Emission Bus (ZEB) Fleet/Infrastructure Analysis | FY21 - Continuing Projects | 235082.54 | 50000 | Jacob/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Definitely will not happen for at least 1 year
BUS | 1715 | Aviat Microwave Update - Santa Rosa Link | FY21 - Continuing Projects | 250000 | 25000 | Jacob/Chi | Likely | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 100% | Low-priority project; should check with Kevin Raddatz but I don't think there's any reason to rush this
BUS | 1931 | Bus Division Office Improvements | FY21 - Continuing Projects | 420000 | 25000 | Jacob/Chi | Unlikely | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 100% | Not sure about this one. Might be good candidate for delay but hesitant to put on list without knowing the full impact.
BUS | 1717 | SRTC Relocation Des/Env | FY21 - Continuing Projects | 2065209 | 300000 | Jacob/Chi | Unlikely | 0 | 0 | 51000 | 249000 | 0 | 0 | 249000 | 300000 | 17% | SRTC project should keep moving
BUS | 1831 | Replace Twenty Paratransit 22' Gas Cutaways | FY21 - Continuing Projects | 2160000 | 750000 | Jacob/Chi | Unlikely | 0 | 0 | 127500 | 622500 | 0 | 0 | 622500 | 750000 | 17% | PO is executed and manufacturer is set to begin production as soon as SIP lifts; should not be delayed
BUS | 1431 | D1 Resurface Employee Parking Lot & Solar Panels | FY21 - Continuing Projects | 5130000 | 50000 | Jacob/Chi | Likely | 10000 | 40000 | 10000 | 40000 | 0 | 0 | 40000 | 50000 | 20% | Won't happen until after D2 project; likely at least 1 year delay
BUS | 1730 | Replace 67 Transit Buses with Hybrids | FY21 - Continuing Projects | 67600000 | 500000 | Jacob/Chi | Unlikely | 0 | 0 | 45062.2559 | 424999.9982 | 28590.5547 | 1347.1893 | 454937.7422 | 499999.9982 | 9.012% | Final punch list items already en route; won't be delayed
BUS | 2133 | SRTC Break Room Renovation | FY21 - New Projects | 39000 | 39000 | Jacob/Chi | Unlikely | 0 | 0 | 39000 | 0 | 0 | 0 | 0 | 39000 | 100% | This project will bring significant operating cost reductions; probably would be counter-productive to delay unless post-COVID operations render it no longer necessary
BUS | 2135 | D2 Bus Operator Breakroom, Dispatch Office, and Restroom Renovation | FY21 - New Projects | 80000 | 50000 | Jacob/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | If D2 pavement and remediation project moves forward, this project should continue as well.
BUS | 2131 | D-1 Bus Admin Bldg Roof, HVAC & Dispatch Rm | FY21 - New Projects | 1700000 | 50000 | Jacob/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Serious maintenance implications but a possible candidate for delay
BUS | 2130 | ZEB Infrastructure Design | FY21 - New Projects | 2000000 | 50000 | Jacob/Chi | Unlikely | 0 | 0 | 10000 | 40000 | 0 | 0 | 40000 | 50000 | 20% | The ZEB study is already underway, we've requested a regulatory extension until March 2021, but even if received we will not be able to delay for a full year
BUS | 2132 | D-2 Pavement & Remediation | FY21 - New Projects | 2000000 | 800000 | Jacob/Chi | Unlikely | 0 | 0 | 160000 | 640000 | 0 | 0 | 640000 | 800000 | 20% | Sensitive project due to need for remediation and operational issues. Should not be delayed without requesting approval from regulatory agency.
BUS | 2134 | Replace Steam Bay Waste Water Recycling System Des/Env | FY21 - New Projects | 100000 | 50000 | Jacob/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | There may be some flexibility but I believe replacement is necessary soon for regulatory reasons
DISTRICT | 2119 | Capital Equipment (FY21) | Capital Equipment | 110000 | 110000 | Jennifer/Chi | Unlikely | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 110000 | 100%
DISTRICT | 2014 | IS Strategic Planning | FY21 - Continuing Projects | 150000 | 75000 | Jennifer/Chi | Unlikely | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 100% | Not a full year delay, but a six month delay may be possible.
DISTRICT | 2013 | Electronic Timekeeping System Upgrade | FY21 - Continuing Projects | 155000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Necessary for function of Kronos, cannot be delayed
DISTRICT | 1913 | Disaster Recovery Improvements (2019) | FY21 - Continuing Projects | 318000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
DISTRICT | 2012 | Cloud Migration Initiative | FY21 - Continuing Projects | 319000 | 75000 | Jennifer/Chi | Unlikely | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 100% | This is an Urgent Project to meet COVID and remote work needs
DISTRICT | 1912 | Manage Detection and Response Services | FY21 - Continuing Projects | 360000 | 50000 | Jennifer/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Lower-priority project
DISTRICT | 2011 | Email to Office 365 Migration | FY21 - Continuing Projects | 375000 | 75000 | Jennifer/Chi | Unlikely | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 75000 | 100%
DISTRICT | 1911 | Cyber Security Improvements | FY21 - Continuing Projects | 408000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
DISTRICT | 1916 | San Rafael A&D Admin Office Improvements | FY21 - Continuing Projects | 471000 | 50000 | Jennifer/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
DISTRICT | 1713 | ADS ACIS data radio replacement | FY21 - Continuing Projects | 700000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | One last SOW remaining and in progress with Procurement, unlikely to delay
DISTRICT | 1816 | Document Management System | FY21 - Continuing Projects | 800000 | 50000 | Jennifer/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Coordinate schedule with Cloud migration project.
DISTRICT | 2010 | Asset Management Strategic Program | FY21 - Continuing Projects | 985000 | 700000 | Jennifer/Chi | Unlikely | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 700000 | 100% | Necessary upgrade, unlikely to delay; coordinate schedule with Cloud migration project.
DISTRICT | 1811 | Hardware/Software for ACIS/INIT | FY21 - Continuing Projects | 1005000 | 500000 | Jennifer/Chi | Unlikely | 0 | 0 | 100000 | 400000 | 0 | 0 | 400000 | 500000 | 20%
DISTRICT | 1812 | Asset and Vehicle Fluid Management System | FY21 - Continuing Projects | 1000000 | 400000 | Jennifer/Chi | Unlikely | 0 | 0 | 80000 | 320000 | 0 | 0 | 320000 | 400000 | 20% | Ongoing
DISTRICT | 1513 | Electronic Timekeeping System | FY21 - Continuing Projects | 1505000 | 10000 | Jennifer/Chi | Unlikely | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 100% | Necessary for function of Kronos, cannot be delayed
DISTRICT | 1712 | Transit Scheduling System | FY21 - Continuing Projects | 2666000 | 250000 | Jennifer/Chi | Unlikely | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 100% | Check with Tony, may be necessary for dispatch and bus operators.
DISTRICT | 1810 | Financial/HR/Payroll Mgmt. Syst | FY21 - Continuing Projects | 4500000 | 500000 | Jennifer/Chi | Unlikely | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 100% | Stagger the start of this project to allow Cloud migration project to define platform technology
DISTRICT | 2017 | Video Conferencing | FY21 - Continuing Projects | 299000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | This project may be already done.
DISTRICT | 1960 | Farebox System Upgrade | FY21 - Continuing Projects | 245000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100%
DISTRICT | 2018 | Financial Management System Upgrade | FY21 - Continuing Projects | 700000 | 250000 | Jennifer/Chi | Likely | 250000 | 0 | 250000 | 0 | 0 | 0 | 0 | 250000 | 100% | This is a big one - not sure if there's an appetite to delay this, but it could be delayed since more urgent upgrade is happening now
DISTRICT | 2110 | On-Site Medical Trailer Infrastructure | FY21 - New Projects | 250000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | I believe this project will be more important with COVID
DISTRICT | 2113 | Trailer B Remodel | FY21 - New Projects | 51000 | 51000 | Jennifer/Chi | Likely | 51000 | 0 | 51000 | 0 | 0 | 0 | 0 | 51000 | 100%
DISTRICT | 2112 | Video Archive | FY21 - New Projects | 20000 | 20000 | Jennifer/Chi | Likely | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 100%
DISTRICT | 2111 | Technology Improvements (2021) | FY21 - New Projects | 240000 | 50000 | Jennifer/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | This is an Urgent Project to meet COVID and remote work needs
FERRY | 2149 | Capital Equipment (FY21) | Capital Equipment | 1918000 | 1918000 | Jacob/Chi | Unlikely | 0 | 0 | 1918000 | 0 | 0 | 0 | 0 | 1918000 | 100% | Ferry capital equipment budget necessary to purchase items critical to operations
FERRY | 0503 | Gangway & Piers - Design | FY21 - Continuing Projects | 11862725 | 150000 | Jacob/Chi | Unlikely | 0 | 0 | 21299.4316 | 120000 | 4312.875 | 4387.6934 | 128700.5684 | 150000 | 14.2% | G&P design budget still needed to push project through permitting phase
FERRY | 1441 | Gangways & Piers - Sausalito Construction | FY21 - Continuing Projects | 22560000 | 100000 | Jacob/Chi | Unlikely | 0 | 0 | 20000 | 80000 | 0 | 0 | 80000 | 100000 | 20% | Project is continuing to be delayed due to permitting, but hope that this won't last another full year
FERRY | 1542 | SLEP: Larkspur, SF, Sausalito | FY21 - Continuing Projects | 1740000 | 50000 | Jacob/Chi | Likely | 5689.6552 | 44310.3448 | 5689.6552 | 40000 | 0 | 4310.3448 | 44310.3448 | 50000 | 11.38% | ENG portion is complete, Ferry portion is currently delayed
FERRY | 1740 | M.S. Sonoma Refurbishment and Repower | FY21 - Continuing Projects | 29196643 | 1500000 | Jacob/Chi | Unlikely | 0 | 0 | 99365.551 | 1200000 | 200634.449 | 0 | 1400634.449 | 1500000 | 6.624% | Sonoma already in dry-docking and nearing completion; wouldn't make sense to delay
FERRY | 1841 | Fuel System Rehab Des/Env | FY21 - Continuing Projects | 1500000 | 200000 | Jacob/Chi | Unlikely | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | Some of this work is necessary due to fuel system emergency; probably should not delay until system is fully stabilized
FERRY | 1842 | Automatic Identification System (AIS) | FY21 - Continuing Projects | 65000 | 10000 | Jacob/Chi | Likely | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 100% | AIS is connected to ferry rehab. Delay may not be possible.
FERRY | 1940 | Purchase New Vessel | FY21 - Continuing Projects | 11000000 | 50000 | Jacob/Chi | Likely | 6500 | 43500 | 6500 | 30000 | 13500 | 0 | 43500 | 50000 | 13% | As already discussed, new vessel likely delayed or cancelled; will impact grant funding
FERRY | 1941 | M.V. Del Norte, M.V. Napa and M.V. Golden Gate Main Engine Overhaul | FY21 - Continuing Projects | 17244866 | 1000000 | Jacob/Chi | Unlikely | 0 | 0 | 200000 | 800000 | 0 | 0 | 800000 | 1000000 | 20% | Projects complete; delay of final work not possible
FERRY | 1944 | Ticketing Systems/TVMs/Door Replacement | FY21 - Continuing Projects | 3219754 | 50000 | Jacob/Chi | Unlikely | 0 | 0 | 10000.0031 | 39999.9969 | 0 | 0 | 39999.9969 | 50000 | 20% | SF and Larkspur portions could be delayed, but grant funding is in jeopardy if Sausalito portion of project is further delayed.
FERRY | 1945 | Renewable Diesel Pilot Program | FY21 - Continuing Projects | 560000 | 25000 | Jacob/Chi | Unlikely | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 100% | This budget may be used for emergency fuel system repairs; hesitant to delay it unless there's a plan for covering these costs elsewhere
FERRY | 2040 | Capital Improvements for Ferry Fleet | FY21 - Continuing Projects | 8385000 | 1000000 | Jacob/Chi | Unlikely | 0 | 0 | 200000 | 800000 | 0 | 0 | 800000 | 1000000 | 20% | Several of these projects are underway and wouldn't make sense to delay, but potentially some individual components of the project could be delayed
FERRY | 2041 | Corte Madera Marsh Restoration Construction | FY21 - Continuing Projects | 3040000 | 50000 | Jacob/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Should check with John Eberle as there are regulatory issues here, but this project hasn't seemed to be a priority this year
FERRY | 2042 | Larkspur Ferry Service and Parking Expansion Env. Clearance and Prelim. Design Study | FY21 - Continuing Projects | 1250000 | 50000 | Jacob/Chi | Unlikely | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Administration is considering whether to delay this project longer; I do not know the current status of that decision
FERRY | 2043 | Water Jet Replacement | FY21 - Continuing Projects | 995000 | 50000 | Jacob/Chi | Likely | 10000 | 40000 | 10000 | 40000 | 0 | 0 | 40000 | 50000 | 20% | Ferry installing water jets via other projects; I don't believe this project is current high priority but should check with Damon
FERRY | 9710 | Corte Madera Marsh Restoration Design | FY21 - Continuing Projects | 2809000 | 50000 | Jacob/Chi | Likely | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | Again, should check with John Eberle to make sure this is okay to delay
FERRY | 2141 | LFT Fuel System Rehabilitation | FY21 - New Projects | 2000000 | 25000 | Jacob/Chi | Likely | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 100% | Additional fuel system work could be delayed
FERRY | 2140 | FY21 Ferry Vessel Rehab | FY21 - New Projects | 4000000 | 1000000 | Jacob/Chi | Likely | 200000 | 800000 | 200000 | 800000 | 0 | 0 | 800000 | 1000000 | 20% | New vessel rehab work is for non-critical repair work; could be delayed
SEISMIC | 1923 | Seismic Phase IIIB - CM/GC | FY21 - Continuing Projects | 9861845.38 | 500000 | Jennifer/Chi | Likely | 0 | 500000 | 0 | 500000 | 0 | 0 | 500000 | 500000 | 0%
SEISMIC | 1528 | GGB Wind Retrofit | FY21 - Continuing Projects | 11860000 | 1000000 | Jennifer/Chi | Likely | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 1000000 | 1000000 | 0%
| 72 Projects |  |  | 483198941.92 | 48660000 |  |  | 1190189.6552 | 2467810.3448 | 19586390.1661 | 27660525.1562 | 1336363.2433 | 76721.4326 | 29073609.8321 | 48659999.9982
*Suggested note for Chi: Please take a broader, brief look at all Divisions, flagging to Jennifer and Jacob all Projects you have already observed delays from your TAM work.
Note on E12: TBanda: Board authorized $355,182 increase 8/21/15. Transferred from JL 1526
Note on E13: jraupach: 3/24/17: Board increased from $3M to $5.9M. Actual increase = $2,928,935. 6/23/17: Board approved increase of $328,065 District. 9/1/17: Increased budget to $6,951,949. 10/27/17: Increased budget to $7,851,949. 7/1/18: Separated Toll Plaza Design from 1525. Reduced budget to $5,942,000.
Note on E16: jraupach: 12/16/16: Board approved increase of $116,495,314 to TPB. 11/22/19: Board approved increase of $250,000 of District Funds 12/23/19: Board approved increase of $194,868 of Cell Site Revenue
Note on E23: jraupach: On 5/26/17 the Board authorized a project budget increase from 1,250,000 to $1,412,000 . With a 162,000 increase in district funding. 6/23/17: Increase of $5,000 for staff time, District funds.
Note on E24: jraupach: 3/28/17: MTC BV pricelist says gas vans are $90,000 each in FY18. 8/27/18 DF Bringing Fourteen (14) Paratransit Buses from FY20 Project List to Adopted FY18/19 Budget. Total Project Budget for 20 Paratransit Buses is $2,160,000 (80%/20% FTA/District).
Note on E26: gkt. On 11/17/16 the Board authorized a FY2017 budget increase of $10,000,000. FTA $8,500,000; State $500,000; District $1,000,000 funds.
Note on E43: Jennifer Raupach: 7/27/18: Budget increase $500,000
Note on E47: Jennifer Raupach: 7/27/18: Budget increase, $364,000.
Note on E48: backup: df 5/26/2017 Board approved 1,385,000 increase in district funding. 7/27/18: Budget increase, $531,000.
Note on E49: JBrown: IS requested to add from FY20 project list on 9/28
Note on E58: gkt. On 11/17/16 the Board authorized a FY2017 budget increase of $3,354,000. FTA $2,683,200; District $670,800 funds. On 5/26/17 the Board authorized an increase of $134,200 to be funded (80% FTA / 17% District / 3% State).
Note on E61: Clifford Duong: 12/19/19: Added $1,000,000 to reflect Budget Increase per resolution 2019-087
Note on F61: Clifford Duong: $1,000,000 increase per board resolution 12/19 2019-087; lease cost will most likely begin to incur CY (FY20)
Note on E65: dferrigno: DF changed per 8/23/18 BO committee staff report

## IS_Schedule_of_Projects
Projects | Summary of the Project | Start Date | End Date | Impacted Departments | IS Lead
1712 - Transit Scheduling System Upgrade- core upgrade | Upgrade of the Hastus application from version 2012 to 2018 and of the underlying infrastructure | In progress | Q1 2020 | Scheduling, Dispatch, Payroll | Barjinder Singh
OP - Technical Upgrade of IFAS | Central Square Technologies has informed the District that they will not continue to host or support IFAS beyond October 2020. This technical upgrade will provide stability to the IFAS system until the new ERP system is implemented. | Q1 2020 | Q2 2020 | Accounting, Payroll, Procurement, Capital & Grants, HR, Bus, Ferry | Robert Leece, Lisa Treat, Marcus Lo
1812 - EJ Ward Upgrade - Phase 1 software upgrade | Upgrade of the fueling system from version 2009 to 2019. Moving to a SaaS solution. | Q1 2020 | Q2 2020 | Bus Maintenance, Ferry Engineering, Bridge (non rev vehicles) | Marcus Lo
1811 - INIT Infrastructure Upgrade/ Virtualization | Virtualizing the underlying servers that the INIT applications because the current hardware is over 10yrs old | Q1 2020 | Q3 2020 | Dispatch, Bus Ops, Bus Maintenance | Tomasz Klys, Min Min Phyo
2010 - Asset Mgt. Strategic Program - Maximo upgraded | Upgrade of Maximo from version 7.5.0.8 to latest version 7.6. | Q1 2020 | Q4 2020 | Bus Maintenance, Procurement, Stores, Ferry Engineering | Lisa Treat, Marcus Lo
1712 - Transit Scheduling System Upgrade - Phase 2 and 3 | Implementation of new features and business process improvements to Hastus 2018 | Q2 2020 | Q1 2021 | Bus Maintenance, Procurement, Stores, Ferry Engineering | Barjinder Singh
CAP - GFI Upgrade | Upgrade of Farebox application from 2008 to latest version. Project will start with business process mapping of the fare structure and development of requirements | Q2 2020 | Q2 2021 | Planning, Bus Maintenance | Tony Scott, Ed Fong
1810 - Financial/ HR/ Payroll Mgmt Syst - Implementation | Replacement of the IFAS (accounting, payroll and HR) system. | Q3 2020 | Q2 2021 | Accounting, Payroll, Procurement, HR, Capital & Grants, | Robert Leece, Joshua Davis
1812 - EJWard upgrade - Phase 2, hardware upgrade | Upgrade of the fuel terminals and CANceivers | Q3 2020 | Q1 2021 | Bus Maintenance, Ferry Engineering, Bridge (non rev vehicles) | Marcus Lo
1816 - Document Management System - Phase 2 (scanned docs into OnBase) | Reducing the amount of paper documents stored in offices across the District by scanning and importing into OnBase. Working with 8 departments | In progress | Q1 2020 | DSO, Marketing, Bus Maintenance, Bus Training, Bus Operations, Capital & Grants, Bridge Managers, HR | Joshua Davis
2010 - Asset Mgt. Strategic Program - Maximo Strategic Roadmap | Maximo vendor working with the District to form a 'to-be' picture for the current version of Maximo V7.6. | In Progress | Q1 2020 | Maximo Users Group | Lisa Treat, Marcus Lo
2014 - IS Strategic Plan | 5 year strategic plan for the Information Systems Department | Q1 2020 | Q2 2020 | All Departments | Fang Lu
1816 - Document Management System - Phase 3 (day forward, workflow) | Establishing a process by which documents are digitally captured and stored in OnBase and can be easily retrieved to avoid the ongoing generation of paper documents | Q1 2020 | Q2 2020 | Bus Maintenance, Bus Training, HR | Joshua Davis
1810 - Financial/ HR/ Payroll Mgmt Syst - RFP Process | RFP process to select a vendor to replace the IFAS (accounting, payroll and HR) system | In progress | Q2 2020 | HR, Accounting, Payroll, Procurement | n/a
2010 - Asset Mgt. Strategic Program - Maximo expansion | Expand the utilization of Maximo to other departments, primarily Bridge. | Q4 2020 | TBD | Bus Maintenance, Procurement, Stores, Ferry Engineering | Lisa Treat, Marcus Lo
1813 Transportation Statistics Reporting | Replacement of the Transtat application. This could be a precursor to a District wide Business Intelligence strategy | TBD | TBD | Planning, Accounting | Tony Scott
OP - Ferry Network improvement and Security Cameras on Boats | Providing network and internet connectivity over the water for each ferry vessel. This is needed for new Verkada security cameras installed on the boats. | In progress | Q2 2020 | Ferry Engineering, Ferry Ops | Jeffrey DiGregorio
OP - SQL AOAG | Moving applications | In progress | Q2 2020 |  | Matt Dacquisto
OP - Bus On Time Performance Reporting | Statistical reporting on bus arrival and departure times. Data can be used by the BUS division to assess delays in bus trips, calculate the cost of each route etc. | In progress | Q2 2020 | Scheduling | Krystal Dong, Tony Clark, Min Min Phyo
OP - Capital & Grants Tool | Internally developed tool to help Capital & Grants team manage Grant allocation and usage, something that cannot be done in the IFAS application and is currently being done in unwieldly spreadsheets. | In progress | Q2 2020 | Capital & Grants | Robert Leece
OP - Road Supervisor Vehicle Tech upgrade | Upgrading the onboard laptops in the Road Supervisor cars | In progress | Q2 2020 | Bus Transportation Supervisors | Ed Fong
2012 Cloud Migration Initiative | Ongoing program to move certain parts of the District's network to the Cloud. | In progress | Q4 2020 | n/a | Ben Valdez
1911 - Cyber Security Improvements | Ongoing program of work to bolster the District's network and infrastructure against cyber security threats | In progress | on going | n/a | Ben Valdez, Tomasz Klys
2016 - Single Sign On | Implementing single sign on for all District enterprise systems. This will mean users will not need separate username and passwords for different applications. | In progress | on going | District | Joe Leong
2017 - Video Conferencing | Installation for video conferencing equipment in key District meeting rooms | In progress | Q4 2020 | District | Joe Leong

## Supporting Asset Information
Attached are assets allocated to each project ID.
DISTRICT CAPITAL PROJECTS |  |  | TERMLite | TERMLite |  |  |  | ASSET MANAGEMENT DATA (IFAS-MAXIMO-ONBASE) - Regional Transit Capital Inventory/National Transit Database | [9 empty] | IFAS
Responsible | Project ID | Project Description | Asset ID | Category | Sub-Category | Unconstrained_Description | 10-YearMaxScore | Mode Code | RTCI_NTD_TERM1302_Description | Date Built | Service Life | 2019_Agency_UsefulLife | Remaining Useful Life | Calculated Condition | Assessed Condition Rating | State of Good Repair | 2019_Replacement Cost | Purchase Cost | CostYr
Jacob/Chi | 2133 | SRTC Break Room Renovation | 32 | Stations | Complete Station | 7836-GGT-SRTC-01 SRTC-D TERMINAL BLDG; (2) CONSESSION BLDGS; PLATEFORM/CANOPY | 66.4286 | MB | 7836-GGT-SRTC-01 SRTC-D TERMINAL BLDG; (2) CONSESSION BLDGS; PLATEFORM/CANOPY | 2008 | 12 | 50 | 76% | 3.8 | 3.33 | IN-SERVICE | 24829486.53 | 16566256 | 2008
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 46 | Stations | Ferry | 7878-GGF-SS-01 SSFT DOCK AND BERTH(float only, does not include leased water way) | 69.8279 | FB | 7878-GGF-SS-01 SSFT DOCK AND BERTH(float only, does not include leased water way) | 1994 | 26 | 50 | 48% | 2.4 | 1.58 | REHAB | 17110692.39 | 15994734 | 2018
Jacob/Chi | 1717 | SRTC Relocation Des/Env | 34 | Stations | Complete Station | 7843-GGT-SRTC-04 SRTC-B CANOPY AND PLATEFORM | 66.4286 | MB | 7843-GGT-SRTC-04 SRTC-B CANOPY AND PLATEFORM | 2008 | 12 | 50 | 76% | 3.8 | 3.35 | IN-SERVICE | 8418453.75 | 5616800 | 2008
Jacob/Chi | 2141 | LFT Fuel System Rehabilitation | 40 | Facilities | Equipment | 7858-GGF-LA-04 LFT-04-1 FUEL STORAGE TANKS 2 MILLION GAL AND FUEL PUMP STATION AND GENERATOR HOUSE | 58.3003 | FB | 7858-GGF-LA-04 LFT-04-1 FUEL STORAGE TANKS 2 MILLION GAL AND FUEL PUMP STATION AND GENERATOR HOUSE | 1974 | 46 | 25 | -84% | 0 | Reinspect | REHAB | 5809554.11 | 5250576.11 | 2017
Jacob/Chi | 1717 | SRTC Relocation Des/Env | 35 | Stations | Complete Station | 7844-GGT-SRTC-05 SRTC-C CANOPY AND PLATEFORM C WITH BUS SHELTER | 66.4286 | MB | 7844-GGT-SRTC-05 SRTC-C CANOPY AND PLATEFORM C WITH BUS SHELTER | 2008 | 12 | 50 | 76% | 3.8 | 3.45 | IN-SERVICE | 6675338.62 | 4453792 | 2008
Jacob/Chi | 1717 | SRTC Relocation Des/Env | 33 | Stations | Complete Station | 7842-GGT-SRTC-03 SRTC-A CANOPY AND PLATEFORM | 66.4286 | MB | 7842-GGT-SRTC-03 SRTC-A CANOPY AND PLATEFORM | 2008 | 12 | 50 | 76% | 3.8 | 3.35 | IN-SERVICE | 4388797.1 | 4102560 | 2018
Jacob/Chi | 1931 | Bus Division Office Improvements | 78 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN BLDG 2 | 53.709 | MB | GGT-SR-01 SAN RAFAEL ADMIN BLDG 2 | 1987 | 33 | 50 | 34% | 1.7 |  | REHAB | 11607908.81 | 3891906.64 | 1987
Jacob/Chi | 9710 | Corte Madera Marsh Restoration Design | 49 | Guideway Elements | Ferry | GGF-LA-00 CORTE MADERA MARSH RESTORATION 1974 (3ACRES) | 63.9956 | FB | GGF-LA-00 CORTE MADERA MARSH RESTORATION 1974 (3ACRES) | 1974 | 46 | 50 | 8% | 0.4 | NA | REHAB | 3144262.99 | 3040000 | 2019
Jacob/Chi | 2134 | Replace Steam Bay Waste Water Recycling System Des/Env | 247 | Facilities | Equipment | GGT-SR-08 SAN RAFAEL WASH RACKS WTR RECLAMATION | 67.4149 | MB | GGT-SR-08 SAN RAFAEL WASH RACKS WTR RECLAMATION | 2013 | 7 | 20 | 65% | 3.25 |  | IN-SERVICE | 3468059.05 | 2738858.01 | 2013
Jennifer/Chi | 2113 | Trailer B Remodel | 2 | Facilities | Buildings | 7748-GGB-SF-11, 12, 13, 14, 15, 16, 17 BR-07 TRAILER OFFICES | 100.0002 | SY | 7748-GGB-SF-11, 12, 13, 14, 15, 16, 17 BR-07 TRAILER OFFICES | 1980 | 40 | 50 | 20% | 1 |  | REHAB | 1762377.98 | 1647435.78 | 2018
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 898 | Stations | Ferry | GGF-SF-10 1978 SF DOCK No_1 | 85.8605 | FB | GGF-SF-10 1978 SF DOCK No_1 | 1978 | 42 | 50 | 16% | 0.8 |  | REHAB | 6346849.59 | 1251007 | 1978
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 899 | Stations | Ferry | GGF-SF-11 1978 SF DOCK No_2 | 61.1003 | FB | GGF-SF-11 1978 SF DOCK No_2 | 1978 | 42 | 50 | 16% | 0.8 |  | REHAB | 6346849.59 | 1251007 | 1978
Jacob/Chi | 2134 | Replace Steam Bay Waste Water Recycling System Des/Env | 13 | Facilities | Equipment | 7798-GGT-SR-08 D1-I BUS WASH RACK | 68.6138 | MB | 7798-GGT-SR-08 D1-I BUS WASH RACK | 1991 | 29 | 20 | -45% | 0 | 2.49 | REHAB | 1311580.55 | 1185384.17 | 2017
Jacob/Chi | 2132 | D-2 Pavement & Remediation | 20 | Facilities | Storage Yard | 7809-GGT-NO-04 D2 NOVATO BUS YARD AND PARKING LOT 1979 | 68.487 | MB | 7809-GGT-NO-04 D2 NOVATO BUS YARD AND PARKING LOT 1979 | 1979 | 41 | 20 | -105% | 0 | Reinspect | REHAB | 813198.66 | 173239.44 | 1979
Jacob/Chi | 1831 | Replace Twenty Paratransit 22' Gas Cutaways | 55 | Vehicles | Revenue Vehicles | 2015 FORD E350 ELDORADO NATIONAL VAN (B0009355 to B0009369) | 71.5003 | DR | 2015 FORD E350 ELDORADO NATIONAL VAN (B0009355 to B0009369) | 2013 | 7 | 10 | 30% | 1.5 |  | REPLACE | 1119199.21 | 945542.36 | 2014
Jennifer/Chi | 2111 | Technology Improvements (2021) | 1165 | Systems | Specialized IT | GGT-SR-09 AVFMS WORK MGT/BUS MAINTENANCE | 62.9003 | SY | GGT-SR-09 AVFMS WORK MGT/BUS MAINTENANCE | 2012 | 8 | 12 | 33.33% | 1.6667 |  | REHAB | 1226740.22 | 936678.08 | 2012
Jacob/Chi | 1931 | Bus Division Office Improvements | 75 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN BLDG 1 | 59.5397 | MB | GGT-SR-01 SAN RAFAEL ADMIN BLDG 1 | 1974 | 46 | 50 | 8% | 0.4 |  | REHAB | 5542290.63 | 832007 | 1974
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 902 | Stations | Ferry | GGF-LA-13 LARKSPUR DOCK No_4 | 61.1003 | FB | GGF-LA-13 LARKSPUR DOCK No_4 | 1995 | 25 | 50 | 50% | 2.5 |  | IN-SERVICE | 1731005.77 | 719606.95 | 1995
Jacob/Chi | 1931 | Bus Division Office Improvements | 79 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN REMODEL | 52.5141 | MB | GGT-SR-01 SAN RAFAEL ADMIN REMODEL | 1989 | 31 | 50 | 38% | 1.9 |  | REHAB | 1667701.44 | 597000 | 1989
Jacob/Chi | 1932 | Zero Emission Bus (ZEB) Fleet/Infrastructure Analysis | 465 | Stations | Complete Station | GGT-SRO-01 SANTA ROSA TERMINAL BLDG | 49.7364 | MB | GGT-SRO-01 SANTA ROSA TERMINAL BLDG | 1990 | 30 | 40 | 25% | 1.25 |  | REHAB | 1580252.71 | 579538.79 | 1990
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 811 | Stations | Buildings | GGF-LA-08 LARKSPUR CUSTOMER LOT 1995 | 41.8098 | FB | GGF-LA-08 LARKSPUR CUSTOMER LOT 1995 | 1995 | 25 | 20 | -25% | 0 |  | REHAB | 1097505.78 | 456250.81 | 1995
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 843 | Stations | Ferry | GGF-LA-10-13 RAMPS&GANGWAY SERVICE LIFEEXT | 78.0149 | FB | GGF-LA-10-13 RAMPS&GANGWAY SERVICE LIFEEXT | 2011 | 9 | 7 | -28.57% | 0 |  | REHAB | 607893.54 | 448766.06 | 2011
Jacob/Chi | 1431 | D1 Resurface Employee Parking Lot & Solar Panels | 16 | Facilities | Buildings | 7804-GGT-SR-13 D1 LOT FOR TRANSIT OPERATIONS | 74.943 | MB | 7804-GGT-SR-13 D1 LOT FOR TRANSIT OPERATIONS | 1978 | 42 | 20 | -110% | 0 |  | REHAB | 1899050.79 | 374315.76 | 1978
Jacob/Chi | 2135 | D2 Bus Operator Breakroom, Dispatch Office, and Restroom Renovation | 17 | Facilities | Buildings | 7806-GGT-NO-01 D2-1 DISPATCH OFFICE 1976 | 55.8764 | MB | 7806-GGT-NO-01 D2-1 DISPATCH OFFICE 1976 | 1976 | 44 | 50 | 12% | 0.6 | 2.44 | REHAB | 379145.53 | 342665.28 | 2017
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 848 | Stations | Ferry | GGF-SF-02 FERRY PASSENGER INFO SYSTEM | 61.1003 | FB | GGF-SF-02 FERRY PASSENGER INFO SYSTEM | 2016 | 4 | 7 | 42.86% | 2.1429 |  | REHAB | 312838.38 | 273362.48 | 2016
Jennifer/Chi | 2012 | Cloud Migration Initiative | 1203 | Systems | Specialized IT | CLOUD INITITIVE-NEW | 53.971 | SY | GGT-SR-05 AVIAT MICROWAVE UPDATES - SANTA ROSA LINK | 2004 | 16 | 12 | -33.33% | 0 |  | REHAB | 276615.08 | 250000 | 2017
Jacob/Chi | 1931 | Bus Division Office Improvements | 86 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN BLDG | 44.952 | MB | GGT-SR-01 SAN RAFAEL ADMIN BLDG | 2003 | 17 | 50 | 66% | 3.3 |  | IN-SERVICE | 475455.5 | 243660.29 | 2003
Jacob/Chi | 2132 | D-2 Pavement & Remediation | 219 | Facilities | Equipment | GGT-NO-01 3M IDENTITY 5100 READER FOR D2 2013 | 65.9914 | MB | GGT-NO-01 3M IDENTITY 5100 READER FOR D2 2013 | 2013 | 7 | 10 | 30% | 1.5 |  | REHAB | 11210.48 | 8853.34 | 2013
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 920 | Stations | Ferry | GGF-LA-08 LARKSPUR OFFSHORE-FENDER | 85.1376 | FB | GGF-LA-08 LARKSPUR OFFSHORE-FENDER | 1977 | 43 | 7 | -514.3% | 0 |  | REHAB | 899259.37 | 167940 | 1977
Jacob/Chi | 1740 | M.S. Sonoma Refurbishment and Repower | 668 | Systems | Ferry | MS SONOMA 1991 SUNDECK | 83.5195 | FB | MS SONOMA 1991 SUNDECK | 1991 | 29 | 7 | -314.3% | 0 |  | REHAB | 423360.06 | 158971 | 1991
Jacob/Chi | 1931 | Bus Division Office Improvements | 80 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN REMODEL | 51.3451 | MB | GGT-SR-01 SAN RAFAEL ADMIN REMODEL | 1991 | 29 | 50 | 42% | 2.1 |  | REHAB | 376403.79 | 141339 | 1991
Jacob/Chi | 2130 | ZEB Infrastructure Design | 292 | Facilities | Major Shops | GGT-SR-08 BUS MAINTENANCE BODY SHOP | 62.6501 | MB | GGT-SR-08 ZERO EMISSION BUS FLEET/INFRASTRUCTURE ANALYSIS | 1980 | 40 | 50 | 20% | 1 |  | REHAB | 129287.13 | 125000 | 2019
Jacob/Chi | 2132 | D-2 Pavement & Remediation | 166 | Facilities | Storage Yard | GGT-NO-04 NOVATO BUS FAC SECURITY IMP 2012 | 68.487 | MB | GGT-NO-04 NOVATO BUS FAC SECURITY IMP 2012 | 2012 | 8 | 20 | 60% | 3 |  | IN-SERVICE | 1459032.26 | 1114044.78 | 2012
Jacob/Chi | 2131 | D-1 Bus Admin Bldg Roof, HVAC & Dispatch Rm | 83 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN HVAC | 74.1127 | MB | GGT-SR-01 SAN RAFAEL ADMIN HVAC | 2000 | 20 | 10 | -100% | 0 |  | REHAB | 231082.7 | 108210.92 | 2000
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 922 | Stations | Ferry | GGF-LA-03 LARKSPUR BILGEWATER SYS | 81.366 | FB | GGF-LA-03 LARKSPUR BILGEWATER SYS | 1989 | 31 | 7 | -342.9% | 0 |  | REHAB | 301155.59 | 107807 | 1989
Jennifer/Chi | 2110 | On-Site Medical Trailer Infrastructure | 983 | Facilities | Buildings | GGB-SF-17 TRAILER REHAB - IS TRAILER | 30.5912 | SY | GGB-SF-17 TRAILER REHAB - IS TRAILER | 2005 | 15 | 50 | 70% | 3.5 |  | IN-SERVICE | 144387.63 | 82619.6 | 2005
Jennifer/Chi | 2014 | IS Strategic Planning | 981 | Systems | Specialized IT | ONE SYSTEM OF RECORD-NEW | 70.1789 | SY | GGB-SF-14 TRAILER REHAB - AUDIT | 2005 | 15 | 50 | 70% | 3.5 |  | IN-SERVICE | 129552.66 | 74130.93 | 2005
Jacob/Chi | 1932 | Zero Emission Bus (ZEB) Fleet/Infrastructure Analysis | 295 | Facilities | Equipment | GGT-SRO-01 SANTA ROSA TERMINAL BLDG | 30.0576 | MB | GGT-SRO-01 SANTA ROSA TERMINAL BLDG | 2006 | 14 | 20 | 30% | 1.5 |  | REHAB | 108261.35 | 65353.52 | 2006
Jacob/Chi | 2132 | D-2 Pavement & Remediation | 149 | Facilities | Storage Yard | GGT-NO-04 NOVATO BUS YARD RESURFACE 1984 | 80.693 | MB | GGT-NO-04 NOVATO BUS YARD RESURFACE 1984 | 1984 | 36 | 20 | -80% | 0 |  | REHAB | 60752.12 | 19401.36 | 1984
Jennifer/Chi | 1713 | ADS ACIS data radio replacement | 975 | Systems | Communications | NEW-ACIS | 45.3791 | SY | GGB-SF-12 TRAILER OFFICE DRAFTING | 2003 | 17 | 50 | 66% | 3.3 |  | IN-SERVICE | 124995.73 | 64057.51 | 2003
Jacob/Chi | 1842 | Automatic Identification System (AIS) | 720 | Systems | Ferry | MS SONOMA 2013 AIS SYSTEM FOR MS SONOMA | 70.5003 | FB | MS SONOMA 2013 AIS SYSTEM FOR MS SONOMA | 2013 | 7 | 7 | 0% | 0 |  | REHAB | 79547.79 | 62821.91 | 2013
Jacob/Chi | 1740 | M.S. Sonoma Refurbishment and Repower | 669 | Systems | Ferry | MS SONOMA 1999 PASSENGER LIFT | 82.8861 | FB | MS SONOMA 1999 PASSENGER LIFT | 1999 | 21 | 7 | -200% | 0 |  | REHAB | 126500.98 | 57978.31 | 1999
Jennifer/Chi | 2010 | Asset Management Strategic Program | 1189 | Systems | Specialized IT | CISCO SWITCH | 62.9003 | SY | CISCO SWITCH | 2009 | 11 | 12 | 8.333% | 0.41667 |  | REHAB | 82531.98 | 56953.99 | 2009
Jacob/Chi | 1842 | Automatic Identification System (AIS) | 721 | Systems | Ferry | MV DEL NORTE 2013 AIS SYSTEM | 70.5003 | FB | MV DEL NORTE 2013 AIS SYSTEM | 2013 | 7 | 7 | 0% | 0 |  | REHAB | 68613.93 | 54187.03 | 2013
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 915 | Stations | Ferry | GGF-LA-10 LARKSPUR DOCK No_1 CYLINDER | 84.4895 | FB | GGF-LA-10 LARKSPUR DOCK No_1 CYLINDER | 2001 | 19 | 7 | -171.4% | 0 |  | REHAB | 111099.73 | 53485.45 | 2001
Jacob/Chi | 1940 | Purchase New Vessel | 976 | Vehicles | Revenue Vehicles | NEW VESSEL TO REPLACE LEASED MILLENIUM | 83.7285 | SY | GGB-SF-15 TRAILER OFFICE 2003 ENGR EXPANSION | 2003 | 17 | 50 | 66% | 3.3 |  | IN-SERVICE | 100332.78 | 51418.3 | 2003
Jennifer/Chi | 2010 | Asset Management Strategic Program | 1187 | Systems | Specialized IT | SWITCH AT BRIDGE DISTRICT DATA ROOM | 62.9003 | SY | SWITCH AT BRIDGE DISTRICT DATA ROOM | 2008 | 12 | 12 | 0% | 0 |  | REHAB | 74120.33 | 49453.15 | 2008
Jacob/Chi | 1842 | Automatic Identification System (AIS) | 722 | Systems | Ferry | MV MENDOCINO 2013 AIS SYSTEM | 70.5003 | FB | MV MENDOCINO 2013 AIS SYSTEM | 2013 | 7 | 7 | 0% | 0 |  | REHAB | 61673.23 | 48705.69 | 2013
Jacob/Chi | 1740 | M.S. Sonoma Refurbishment and Repower | 670 | Systems | Ferry | MS SONOMA 2002 LIFE RAFT REPLACEMENT | 80.5829 | FB | MS SONOMA 2002 LIFE RAFT REPLACEMENT | 2002 | 18 | 7 | -157.1% | 0 |  | REHAB | 97250.33 | 48444.53 | 2002
Jacob/Chi | 2131 | D-1 Bus Admin Bldg Roof, HVAC & Dispatch Rm | 82 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN HVAC | 75.6957 | MB | GGT-SR-01 SAN RAFAEL ADMIN HVAC | 1998 | 22 | 10 | -120% | 0 |  | REHAB | 105863.4 | 47550.08 | 1998
Jacob/Chi | 1717 | SRTC Relocation Des/Env | 362 | Stations | Complete Station | GGT-SRTC-01 SR TRANSIT CENTER SIGNS | 67.8026 | MB | GGT-SRTC-01 SR TRANSIT CENTER SIGNS | 1996 | 24 | 40 | 40% | 2 |  | REHAB | 104407.89 | 44734.43 | 1996
Jennifer/Chi | 1811 | Hardware/Software for ACIS/INIT | 1087 | Systems | Communications | VIRTUAL TAPE LIBRARY | 45.3791 | SY | VIRTUAL TAPE LIBRARY | 2007 | 13 | 12 | -8.333% | 0 |  | REHAB | 56777.4 | 36625.78 | 2007
Jennifer/Chi | 1911 | Cyber Security Improvements | 1086 | Systems | Communications | SECURITY IMPROVEMENTS | 47.4189 | SY | VIRTUAL TAPE LIBRARY | 2007 | 13 | 12 | -8.333% | 0 |  | REHAB | 56777.4 | 36625.78 | 2007
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 926 | Stations | Ferry | GGF-SS-01 OIL BOOM REEL No_1 | 85.8395 | FB | GGF-SS-01 OIL BOOM REEL No_1 | 2014 | 6 | 7 | 14.29% | 0.71429 |  | REHAB | 35416.26 | 28928.84 | 2014
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 927 | Stations | Ferry | GGF-SS-01 OIL BOOM REEL No_2 | 85.2503 | FB | GGF-SS-01 OIL BOOM REEL No_2 | 2014 | 6 | 7 | 14.29% | 0.71429 |  | REHAB | 35416.26 | 28928.84 | 2014
Jacob/Chi | 1740 | M.S. Sonoma Refurbishment and Repower | 785 | Systems | Ferry | MS GENERATOR SET | 52.4599 | FB | MS GENERATOR SET | 1985 | 35 | 7 | -400% | 0 |  | REHAB | 85657.77 | 27969 | 1985
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 921 | Stations | Ferry | GGF-SF-10-13 1988 SF DOCK SAFETY PLATFORM | 85.1376 | FB | GGF-SF-10-13 1988 SF DOCK SAFETY PLATFORM | 1988 | 32 | 7 | -357.1% | 0 |  | REHAB | 67293.32 | 23500 | 1988
Jacob/Chi | 1740 | M.S. Sonoma Refurbishment and Repower | 728 | Systems | Ferry | MS SONOMA 1993 SHAFT SEALS SPARE | 98.0129 | FB | MS SONOMA 1993 SHAFT SEALS SPARE | 1993 | 27 | 7 | -285.7% | 0 |  | REHAB | 50508.04 | 19991.4 | 1993
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 694 | Stations | Ferry | GGF-LA-10-13 3x5 FENDER & SECURING LINE | 64.3558 | FB | GGF-LA-10-13 3x5 FENDER & SECURING LINE | 2013 | 7 | 7 | 0% | 0 |  | REHAB | 24997.53 | 19741.5 | 2013
Jacob/Chi | 2132 | D-2 Pavement & Remediation | 161 | Facilities | Storage Yard | GGT-NO-04 NOVATO BUS YARD RESURFACE 2004 | 68.487 | MB | GGT-NO-04 NOVATO BUS YARD RESURFACE 2004 | 2004 | 16 | 20 | 20% | 1 |  | REHAB | 123286.03 | 64801.36 | 2004
Jacob/Chi | 2132 | D-2 Pavement & Remediation | 164 | Facilities | Storage Yard | GGT-NO-04 NOVATO BUS YARD SECURITY 2007 | 68.487 | MB | GGT-NO-04 NOVATO BUS YARD SECURITY 2007 | 2007 | 13 | 20 | 35% | 1.75 |  | REHAB | 26952.36 | 17386.34 | 2007
Jennifer/Chi | 1810 | Financial/HR/Payroll Mgmt Syst | 980 | Systems | Specialized IT | ENTERPRISE RESOUCE PLANNING SYS -NEW | 58.2651 | SY | GGB-SF-13 PRINTER-LASERJET COLOR HP5550NTRAILER REHAB - CONSULTANT | 2005 | 15 | 50 | 70% | 3.5 |  | IN-SERVICE | 27048.64 | 15477.42 | 2005
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 916 | Stations | Ferry | GGF-LA-10 LARKSPUR DOCK No_1 CYLINDER | 61.1003 | FB | GGF-LA-10 LARKSPUR DOCK No_1 CYLINDER | 2001 | 19 | 7 | -171.4% | 0 |  | REHAB | 30641.21 | 14751.24 | 2001
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 918 | Stations | Ferry | GGF-LA-11 LARKSPUR DOCK No_2 CYLINDE | 61.1003 | FB | GGF-LA-11 LARKSPUR DOCK No_2 CYLINDE | 2001 | 19 | 7 | -171.4% | 0 |  | REHAB | 30641.19 | 14751.23 | 2001
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 690 | Stations | Ferry | GGF-LA-02 10-IN X16-IN WET BANDSAW & 28-IN VERT | 69.6456 | FB | GGF-LA-02 10-IN X16-IN WET BANDSAW & 28-IN VERT | 2011 | 9 | 7 | -28.57% | 0 |  | REHAB | 19950.39 | 14728 | 2011
Jacob/Chi | 2131 | D-1 Bus Admin Bldg Roof, HVAC & Dispatch Rm | 117 | Facilities | Buildings | GGT-SR-01 SAN RAFAEL ADMIN HVAC 1997 | 55.5438 | MB | GGT-SR-01 SAN RAFAEL ADMIN HVAC 1997 | 1997 | 23 | 10 | -130% | 0 |  | REHAB | 33490.67 | 14696.09 | 1997
Jennifer/Chi | 2018 | Financial Management System Upgrade | 1194 | Systems | Specialized IT | GGF-LA-01 FATPIPE MPVPN APPLIANCE | 58.2651 | SY | GGF-LA-01 FATPIPE MPVPN APPLIANCE | 2014 | 6 | 20 | 70% | 3.5 |  | IN-SERVICE | 15518.96 | 12676.25 | 2014
Jacob/Chi | 2131 | D-1 Bus Admin Bldg Roof, HVAC & Dispatch Rm | 121 | Facilities | Buildings | GGT-SR-01 HVAC UNIT-DISPATCH OFFICE 2010 | 61.5145 | MB | GGT-SR-01 HVAC UNIT-DISPATCH OFFICE 2010 | 2010 | 10 | 10 | 0% | 0 |  | REHAB | 16440.34 | 11734.32 | 2010
Jennifer/Chi | 2010 | Asset Management Strategic Program | 1188 | Systems | Specialized IT | CISCO SWITCH | 62.9003 | SY | CISCO SWITCH | 2009 | 11 | 12 | 8.333% | 0.41667 |  | REHAB | 14490.98 | 9999.99 | 2009
Jacob/Chi | 2131 | D-1 Bus Admin Bldg Roof, HVAC & Dispatch Rm | 122 | Facilities | Buildings | GGT-SR-05 CARRIER HVAC SYSTEM 2012 | 59.3003 | MB | GGT-SR-05 CARRIER HVAC SYSTEM 2012 | 2012 | 8 | 10 | 20% | 1 |  | REHAB | 12376.39 | 9450 | 2012
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 847 | Stations | Ferry | GGF-LA-02 PETRO BARRIER FLOAT SET | 61.1003 | FB | GGF-LA-02 PETRO BARRIER FLOAT SET | 2015 | 5 | 7 | 28.57% | 1.4286 |  | REHAB | 11010.39 | 9302 | 2015
Jacob/Chi | 2132 | D-2 Pavement & Remediation | 273 | Facilities | Equipment | GGT-NO-05 NOVATO FUEL TANKS 2003 | 61.7424 | MB | GGT-NO-05 NOVATO FUEL TANKS 2003 | 2003 | 17 | 25 | 32% | 1.6 |  | REHAB | 224931.22 | 115272.21 | 2003
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 923 | Stations | Ferry | GGF-SF-10-14 1990 SF DOCK POWER GROUND | 81.366 | FB | GGF-SF-10-14 1990 SF DOCK POWER GROUND | 1990 | 30 | 7 | -328.6% | 0 |  | REHAB | 22175.83 | 8132.72 | 1990
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 693 | Stations | Ferry | GGF-LA-10-13 DONUT FENDER & PILE EXT-LA | 67.1857 | FB | GGF-LA-10-13 DONUT FENDER & PILE EXT-LA | 2012 | 8 | 7 | -14.29% | 0 |  | REHAB | 9951.4 | 7598.4 | 2012
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 909 | Stations | Ferry | GGF-LA-10-13 FOAM FILLED FENDER 5-FT X 8-FT | 51.9195 | FB | GGF-LA-10-13 FOAM FILLED FENDER 5-FT X 8-FT | 2017 | 3 | 7 | 57.14% | 2.8571 |  | IN-SERVICE | 7732.61 | 6988.6 | 2017
Jacob/Chi | 2131 | D-1 Bus Admin Bldg Roof, HVAC & Dispatch Rm | 118 | Facilities | Buildings | GGT-SR-05 SAN SAN RAFAEL COMPUTER RM HVAC 2005 | 76.3782 | MB | GGT-SR-05 SAN SAN RAFAEL COMPUTER RM HVAC 2005 | 2005 | 15 | 10 | -50% | 0 |  | REHAB | 11048.17 | 6321.84 | 2005
Jennifer/Chi | 2011 | Email to Office 365 Migration | 977 | Systems | Specialized IT | NEW-OFFICE365 | 0 | SY | GGT-SR-05 TRAILER OFFICE REHAB | 2003 | 17 | 50 | 66% | 3.3 |  | IN-SERVICE | 11885.32 | 6090.96 | 2003
Jacob/Chi | 1717 | SRTC Relocation Des/Env | 361 | Stations | Complete Station | GGT-SRTC-01 SR TRANSIT CENTER BENCHS | 69.085 | MB | GGT-SRTC-01 SR TRANSIT CENTER BENCHS | 1994 | 26 | 40 | 35% | 1.75 |  | REHAB | 14369.69 | 5819.22 | 1994
Jacob/Chi | 1542 | SLEP: Larkspur, SF, Sausalito | 919 | Stations | Ferry | GGF-LA-08 FENDERING SYSTEM | 61.1003 | FB | GGF-LA-08 FENDERING SYSTEM | 1972 | 48 | 7 | -585.7% | 0 |  | REHAB | 39117.28 | 5000 | 1972
Jennifer/Chi | 2018 | Financial Management System Upgrade | 1382 | Systems | Communications | IFAS | 0 |  |  | 2009 | 11 | 10 | -10% | 0 |  | REPLACE OR REHAB
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.